## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of BRAHAMOTTAR MANIKCHAK ground water based water supply scheme under Block- LALGOLA, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000060/2023-2024 | 3777/MEDB | 03/11/2023 | 03/02/2024 | GANGULI ELECTRICAL CO. | 12.01 | 0 | 0 | 10
2 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 201/BD-1/9 | 10/02/2024 | 10/02/2024 | Resource Division | 31.4 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 1510/BD-I/1 | 12/09/2024 | 12/09/2024 | Resource Division | 4.13 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Quotation for Brahamatter PH-1 Application No- 3004544380 Ref ID- 304228570 |  |  | BILL/01170/2023-2024 | 240/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 7.62 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Augmentation of Brohmottar Manikchak Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000203/2023-2024 | 848/BD-I | 05/09/2023 | 01/04/2025 | M/S TAPAS KUMAR CHAKRABORTY | 458.37 | 0 | 0 | 50
6 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BRAHIMOTTAR MANIKCHAK Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer |  | ORD/000280/2024-2025 | 10/BD-I | 06/01/2025 | 21/01/2025 | HARUN ALL RASHID & BROTHERS | 8.92 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000570/2024-2025 | 385/MEDB | 12/02/2025 | 12/05/2025 | SAMARPITA ENGINEERING | 12.11 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BRAHAMOTTAR MANIKCHAK Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000262/2022-2023 | 1685/BD-I | 14/03/2023 | 24/03/2023 | ENVIROTECH SOLUTIONS | 2.6 | 0 | 0 | 1
9 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Brahamottar Manikchak Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000034/2023-2024 | 126/BD-I | 12/05/2023 | 11/06/2023 | HARUN ALL RASHID & BROTHERS | 8.9 | 0 | 0 | 100
10 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) of Ground water supply scheme for Brahamottar Manikchak of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000264/2023-2024 | 986/BD-I | 30/10/2023 | 20/02/2025 | PROSENJIT DAS | 8.57 | 0 | 0 | 100
Total | [13 empty] | 554.63 | 0 | 0