## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of MAKIMNAGAR ground water based water supply scheme under Block- LALGOLA, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000065/2023-2024 | 3780/MEDB | 03/11/2023 | 03/02/2024 | JOY BISHNU ENGINEERING CO. | 11.98 | 10.05 | 83.88 | 10
2 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | Repair And Renovation Works Of OHR (180 Cum) of Ground Water Based Supply Scheme for Makimnagar of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | JE | ORD/000274/2023-2024 | 992/BD-I | 30/10/2023 | 29/11/2023 | MATIUR RAHAMAN | 8.07 | 3.67 | 45.44 | 65
3 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 201/BD-1/11 | 10/02/2024 | 10/02/2024 | Resource Division | 36.15 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 1510/BD-I/2 | 12/09/2024 | 12/09/2024 | Resource Division | 6.78 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | MAKIMNAGAR PH-1 |  |  | BILL/01515/2023-2024 | 403/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 12.14 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | Augmentation of Makimnagar Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000158/2023-2024 | 682/BD-I | 10/08/2023 | 07/08/2025 | M/S BIMALENDU BOSE | 427.29 | 0 | 0 | 30
7 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | MAKIMNAGAR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000452/2023-2024 | 455/BD-I | 15/03/2024 | 14/05/2024 | M/S UNIVERSAL TRADING | 22.87 | 18.79 | 82.16 | 50
8 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | Construction of Pump House Cum Chlorine Room at Head Work site of MOKIMNAGAR PWSS (H/W Site & 2nd Site) under Jal Jevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer |  | ORD/000008/2025-2026 | 595/BD-I | 22/04/2025 | 21/06/2025 | M/S MEGHNA CONSTRUCTION | 12.78 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MOKIMNAGAR Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer |  | ORD/000363/2024-2025 | 318/BD-I | 24/02/2025 | 11/03/2025 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MAKIMNAGAR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000263/2022-2023 | 1686/BD-I | 14/03/2023 | 24/03/2023 | ENVIROTECH SOLUTIONS | 2.59 | 2.62 | 101 | 1
Total | [13 empty] | 549.67 | 35.13 | 6.39