## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 194/BD-I/7 | 09/02/2024 | 09/02/2024 | Resource Division | 32.78 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | LOAD ENHANCEMENT AT BANSGARA Z2 PH1 ID 312397840 |  |  | BILL/01637/2023-2024 | 481/WBSEDCL-JJM | 21/03/2024 | 21/03/2024 | WBSEDCL | 1.8 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | LOAD ENHANCEMENT BANSGARA AIRP ID 3004571720 |  |  | BILL/01638/2023-2024 | 482/WBSEDCL-JJM | 21/03/2024 | 21/03/2024 | WBSEDCL | 1.11 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | load enhancement bansgara z2 ph 1 |  |  | BILL/01597/2023-2024 |  | 05/03/2024 | 05/03/2024 | WBSEDCL | 1.8 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Augmentation of Bansgara Zone-II Piped water supply scheme to accommodate construction of Arsenic cum Iron Removal Plant(AIRP), pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000025/2023-2024 | 313/BD-I | 14/06/2023 | 22/03/2026 | MODERN CONSTRUCTION | 261.29 | 0 | 0 | 70
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Raninagar-II under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000538/2024-2025 | 324/MEDB | 10/02/2025 | 31/12/2025 | JOGMAYA ENGINEERING | 24.94 | 0 | 0 | 25
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Construction of Service Road, Improvement of RCC OHR and Pump House of Bansgara Zone-II PWSS under Jal Jeevan Mission within Raninagar-II block under Berhampore Division-I PHE Dte. in the district of Murshidabad. | Assistant Engineer |  | ORD/000097/2025-2026 | 1014/BD-I | 06/08/2025 | 20/09/2025 | GOUTAM MANDAL | 32.21 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA ZONE-II Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000277/2022-2023 | 1760/BD-I | 24/03/2023 | 03/04/2023 | M/S SOBHA & CO | 2.46 | 0 | 0 | 100
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bansgara Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte | Assistant Engineer | Junior Engineer-II | ORD/000313/2023-2024 | 1149/BD-I | 04/12/2023 | 03/01/2024 | NADIA TUBEWELLS | 11.56 | 0 | 0 | 100
Total | [13 empty] | 369.95 | 0 | 0