## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | Augmentation of Moktarpur Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000205/2023-2024 | 871/BD-I | 12/09/2023 | 18/07/2024 | MS RUBIET HOSSAIN | 333.41 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MOKTARPUR Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000274/2022-2023 | 1758/BD-I | 24/03/2023 | 03/04/2023 | M/S SOBHA & CO | 2.67 | 2.67 | 100 | 100
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 61/BD-1/7 | 27/04/2023 | 27/04/2023 | Resource Division | 37.29 | 0 | 0 | 0
4 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 15.12 | 2.1 | 20
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | Construction of Service Road for approach and Pump House at Augnentation of MUKTARPUR PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer |  | ORD/000093/2024-2025 | 1306/BD-I | 07/08/2024 | 06/10/2024 | M/S BHAGIRATHI ENTERPRISE | 7.65 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | Improvement of OHR (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Muktarpur of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer | JE | ORD/000001/2024-2025 | 889/BD-I | 06/06/2024 | 03/12/2024 | NOBEL CONSTRUCTION | 9.28 | 6.68 | 71.95 | 90
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | AT MOKTARPUR PH 2 ID 304244960 |  |  | BILL/01478/2023-2024 | 375/WBSEDCL-JJM | 21/02/2024 | 21/02/2024 | WBSEDCL | 3.92 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | LOAD ENHANCEMENT OF MOKTARPUR PWSS ID 312350581 |  |  | BILL/01624/2023-2024 | 460/WBSEDCL-JJM | 18/03/2024 | 18/03/2024 | WBSEDCL | 1.03 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | load enhancement moktarpur pwss |  |  | BILL/01599/2023-2024 |  | 05/03/2024 | 05/03/2024 | WBSEDCL | 1.03 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | AT MOKTARPUR PH 1 ID 304244961 |  |  | BILL/01477/2023-2024 | 374/WBSEDCL-JJM | 21/02/2024 | 21/02/2024 | WBSEDCL | 12.51 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of MUKTARPUR ZONE-II PWSS under Jal Jeevan Mission within Raninagar -I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000075/2025-2026 | 842/BD-I | 23/06/2025 | 22/08/2025 | GOUTAM KUMAR CHAUDHURI | 19 | 0 | 0 | 0
12 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | Augmentation | MOKTARPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer |  | ORD/000070/2025-2026 | 824/BD-I | 18/06/2025 | 02/08/2025 | BURIMAA CONSTRUCTION | 23.3 | 0 | 0 | 0
Total | [13 empty] | 1171.31 | 24.47 | 2.09