## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 61/BD-1/10 | 27/04/2023 | 27/04/2023 | Resource Division | 30.97 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 201/BD-1/22 | 10/02/2024 | 10/02/2024 | Resource Division | 83.89 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | NEW SERVICE CONNECTION AT BANSGARA Z1 PH 1 ID 304268983 |  |  | BILL/01129/2024-2025 |  | 26/11/2024 | 26/11/2024 | WBSEDCL | 11.36 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | Augmentation of BANSGARA ZONE-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | Junior Engineer-I | ORD/000142/2023-2024 | 628/BD-I | 04/08/2023 | 09/06/2024 | SUNIL RABI DAS | 388.8 | 242.14 | 62.28 | 10
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Bansgara Zone-I of Raninagar-II block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | Junior Engineer-II | ORD/000248/2023-2024 | 1032/BD-I | 01/11/2023 | 01/12/2023 | ALOK BANERJEE ENTERPRISE | 6.83 | 4.46 | 65.31 | 80
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Bansgara Zone-I PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000045/2024-2025 | 1068/BD-I | 03/07/2024 | 29/04/2025 | MAHATO ENTERPRISE | 9 | 0 | 0 | 75
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | BANSGARA ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | Junior Engineer-I | ORD/000084/2024-2025 | 1245/BD-I | 30/07/2024 | 26/01/2025 | M.K.CONSTRUCTION | 22.29 | 0 | 0 | 30
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | Construction of Service Road & extension of boundary wall of Bansgara Zone-I PWSS under Jal Jeevan Mission within Raninagar-II block under Berhampore Division-I PHE Dte. in the district of Murshidabad. | Assistant Engineer |  | ORD/000076/2025-2026 | 843/BD-I | 23/06/2025 | 07/08/2025 | SUBHRANIL DAS | 17.81 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000264/2022-2023 | 1687/BD-I | 14/03/2023 | 24/03/2023 | ENVIROTECH SOLUTIONS | 2.73 | 2.76 | 101 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000276/2022-2023 | 1759/BD-I | 24/03/2023 | 03/04/2023 | M/S SOBHA & CO | 2.6 | 2.6 | 100 | 100
11 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | EW SERVICE CONNECTION AT BANSGARA Z1 PH 1 ID 304268983 |  |  | BILL/01135/2024-2025 | 280/WBSEDCL-JJM | 29/11/2024 | 29/11/2024 | WBSEDCL | 11.36 | 0 | 0 | 0
12 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 15.84 | 2.2 | 20
Total | [13 empty] | 1307.86 | 267.8 | 20.48