## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . | SM/14739 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 61/BD-1/11 | 27/04/2023 | 27/04/2023 | Resource Division | 26.29 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . | SM/14739 | Augmentation | AT UDAY NAGAR DIAR PH 2 ID 304244356 |  |  | BILL/01480/2023-2024 | 373/WBSEDCL-JJM | 21/02/2024 | 21/02/2024 | WBSEDCL | 3.85 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . | SM/14739 | Augmentation | Augmentation of Udaynagar Diar Piped water supply scheme to accommodate construction of Pump House ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000214/2022-2023 | 1551/BD-I | 17/02/2023 | 06/02/2025 | BISWAS CONSTRUCTION | 82.74 | 0 | 0 | 75
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . | SM/14739 | Augmentation | Balance work of Boundary Wall at Augmentation of Udaynagar Diar PWSS of Jalangi Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer |  | ORD/000028/2024-2025 | 984/BD-I | 19/06/2024 | 03/08/2024 | BISWAS CONSTRUCTION | 11.94 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . | SM/14739 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for UDAYNAGARDIAR Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000281/2022-2023 | 1559/BD-I | 20/02/2023 | 02/03/2023 | M/S SOBHA & CO | 2.53 | 0 | 0 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . | SM/14739 | Augmentation | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for UdaynagarDiar of Jalangi block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | JE | ORD/000290/2023-2024 | 1037/BD-I | 03/11/2023 | 29/08/2025 | PRANAB KUMAR SAHA | 6.34 | 0 | 0 | 100
Total | [13 empty] | 133.7 | 0 | 0