## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 61/BD-1/5 | 27/04/2023 | 27/04/2023 | Resource Division | 49.26 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-I under Hurshi ground water based water supply scheme under Block_ Raninagar-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000673/2023-2024 | 4297/MEDB | 29/12/2023 | 29/03/2024 | SREE RADHA ELECTRICAL | 34.27 | 28.43 | 82.96 | 80
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Hurshi New PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer |  | ORD/000048/2024-2025 | 1110/BD-I | 10/07/2024 | 08/09/2024 | PRADIP DAS | 8.04 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | Augmentation | NEW SERVICE CONNECTION AT HURSHI z1 ph2 id 304247241 |  |  | BILL/01128/2024-2025 |  | 26/11/2024 | 26/11/2024 | WBSEDCL | 9.34 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | Augmentation | NEW CONNECTION HURSHI Z-1 PH-I |  |  | BILL/01632/2023-2024 | 469/WBSEDCL-JJM | 19/03/2024 | 19/03/2024 | WBSEDCL | 7.8 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | Augmentation | Augmentation of Hurshi Zone-I Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant( AIRP), pump house and boundary wall , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000196/2023-2024 | 844/BD-I | 05/09/2023 | 17/05/2025 | M/S B.M. INDUSTRIES | 423.99 | 190.56 | 44.94 | 70
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HURSHI ZONE-I Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000268/2022-2023 | 1691/BD-I | 14/03/2023 | 24/03/2023 | RADIANT | 2.6 | 2.6 | 100 | 100
8 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hurshi Zone-I Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 3 nos Tubewell) | Assistant Engineer | JE | ORD/000315/2023-2024 | 1147/BD-I | 04/12/2023 | 03/01/2024 | MAMATA USHA ENTERPRISE | 34.71 | 9.7 | 27.94 | 50
9 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | Augmentation | Repair And Renovation Works Of OHR (180 Cum) of Ground Water Based Supply Scheme for Hurshi Zone-I of Raninagar-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | JE | ORD/000298/2023-2024 | 1066/BD-I | 21/11/2023 | 12/01/2025 | M/S ADHIKARI CONSTRUCTION | 7.79 | 5.62 | 72.18 | 100
Total | [13 empty] | 577.8 | 236.92 | 41