## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for ANDULBERIA Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000296/2022-2023 | 1648/BD-I | 10/03/2023 | 20/03/2023 | TECHVISION | 2.81 | 2.8 | 99.83 | 100
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Allied works of Laying of distribution pipeline of ANDULBERIA ZONE-I piped water supply scheme under JJM within Beldanga-II Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | Assistant Engineer-II |  | ORD/000127/2024-2025 | 1477/BD-I | 06/09/2024 | 05/11/2024 | SUSHANTA MANDAL | 45.66 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 196/BD-I/23 | 09/02/2024 | 09/02/2024 | Resource Division | 64.29 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Augmentation of Andulberia Zone_I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000255/2022-2023 | 1661/BD-I | 13/03/2023 | 02/03/2025 | M/S BIMALENDU BOSE | 433.78 | 433.17 | 99.86 | 100
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Construction of Boundary wall at 2nd & 3rd Tube Well Site of ANDULBERIYA ZONE -I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000013/2025-2026 | 600/BD-I | 22/04/2025 | 21/06/2025 | AICH CONSTRUCTION | 20.36 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Repair And Renovation Works Of R.C.C Elevated Reservoir (700 Cum) for Andulberia Zone-I water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal Jeevan Mission. | Assistant Engineer-II | JE | ORD/000360/2023-2024 | 18/BD-I | 04/01/2024 | 27/11/2024 | A.S CONSTRUCTION | 11.02 | 0 | 0 | 100
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDULBERIA ZONE-I Water Supply Scheme(TW-II) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-II | JE | ORD/000278/2024-2025 | 12/BD-I | 06/01/2025 | 20/07/2025 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0 | 100
8 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 139 Cum/hr.) with allied work at Andulberia Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer-II | JE | ORD/000015/2024-2025 | 916/BD-I | 07/06/2024 | 04/11/2024 | M/S GOUTAM CHAKRABORTY | 47.44 | 12.56 | 26.47 | 100
9 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Balance work for Improvement of Existing AIRP of (Capacity 139 Cum/hr,with allied work at Andulberia Zone-IWater Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I,P.H.Engineering Dte. In the district of Murshidabad. | Assistant Engineer-II | JE | ORD/000054/2025-2026 | 763/BD-I | 22/05/2025 | 21/06/2025 | M/S GOUTAM CHAKRABORTY | 11.84 | 0 | 0 | 100
10 | MURSHIDABAD |  | Central Drilling | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21985.97 | 448.53 | 2.04