## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14922 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000238/2022-2023 | 1596/BD-I | 28/02/2023 | 10/03/2023 | TECHVISION | 2.81 | 2.81 | 100 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14922 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000003/2023-2024 | 32/BD-I | 19/04/2023 | 29/04/2023 | TECHVISION | 2.81 | 2.81 | 100 | 100
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14922 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1156/BD-I | 05/12/2023 | 05/12/2023 | Resource Division | 47.43 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14922 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of BALI ZONE-II Water Supply Scheme under Jal Jevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer-II | JE | ORD/000299/2024-2025 | 148/BD-I | 29/01/2025 | 30/03/2025 | SUPRIYA DEY | 8.77 | 0 | 0 | 60
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14922 | Augmentation | Augmentation of Bali Zone_II Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. [2nd Call for WBPHED/EE/BD-I/NIeT-27 of 2022 ¿ 2023(sl-19)] | Assistant Engineer-II | JE | ORD/000114/2023-2024 | 376/BD-I | 28/06/2023 | 25/12/2023 | S.D PROJECT | 385.38 | 310.84 | 80.66 | 43
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14922 | Augmentation | Relaying of different dia upvc distribution system inbetween unlaid portion Shyamnagar, kamrapara, Dargatala, Mathpara, Haldarpara, Munsipara and near Shyamnagar H.S. and Shymnagar Bridge of Bali Zone-II Water supply scheme under JJM under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | JE | ORD/000443/2023-2024 | 442/BD-I | 15/03/2024 | 14/04/2024 | SUJAUDDIN SHAIKH | 4.59 | 4.37 | 95.11 | 100
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14922 | Augmentation | Improvement of OHR (550 Cum) Extension of Boundary Wall & Service Road for Augmentation of Bali Zone-II PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad | Assistant Engineer-II | JE | ORD/000062/2024-2025 | 1179/BD-I | 25/07/2024 | 20/03/2025 | SUMAN CHOWDHURY | 19.54 | 0 | 0 | 90
Total | [13 empty] | 471.33 | 320.82 | 68.07