## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 201/BD-1/10 | 10/02/2024 | 10/02/2024 | Resource Division | 43.36 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 1510/BD-I/3 | 12/09/2024 | 12/09/2024 | Resource Division | 2.27 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | JUMRA NAYAGRAM PH-1 |  |  | BILL/01516/2023-2024 | 400/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 5.31 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) of Ground water supply scheme for Jumra Nayagram of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,Assistant Engineer-I | Junior Engineer | ORD/000262/2023-2024 | 984/BD-I | 30/10/2023 | 29/11/2023 | AJOY GHOSH | 8.56 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM (PART-B) ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000542/2024-2025 | 328/MEDB | 10/02/2025 | 10/05/2025 | MERCURY ENGINEERING CO | 22.71 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | Bored Cast-in-situ_M30_grade 450 mm. dia. 22.00 m (Shaft Length) R.C.C pile for construction of OHR at Head work site of Jhumra Nayagram Ground Piped Water Supply Scheme under Jal Jeevan Mission of Lalgola Block, Murshidabad district under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000090/2024-2025 | 1302/BD-I | 07/08/2024 | 05/03/2025 | AICH CONSTRUCTION | 26.19 | 0 | 0 | 100
7 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | Balance works i.c.w of Existing AIRP (Modified Sujapur Sadipur Model) capacity 53.12 cum/hr at Head Work Site of Jhumra Nayagram Water Supply Scheme under JJM within Lalgola block under Berhampore Division -I, P.H.E. Dte. In the district of Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000074/2025-2026 | 841/BD-I | 23/06/2025 | 23/07/2025 | GITA CONSTRUCTION | 26.5 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for JUMRA NAYAGRAM Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000260/2022-2023 | 1683/BD-I | 14/03/2023 | 24/03/2023 | ENVIROTECH SOLUTIONS | 2.6 | 2.6 | 100.29 | 1
9 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jumra Nayagram Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | Assistant Engineer,Assistant Engineer-I | JE,Junior Engineer | ORD/000038/2023-2024 | 140/BD-I | 12/05/2023 | 06/04/2025 | HARUN ALL RASHID & BROTHERS | 17.82 | 8.41 | 47.2 | 50
10 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Jumra Nayagram ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) Augmentation of PWSS under Jal Jeevan Mission. | Assistant Engineer | JE | ORD/000320/2023-2024 | 1161/BD-I | 05/12/2023 | 04/01/2024 | M/S. RAY ORDER SUPPLIER AND CONTRACTOR | 2.92 | 1.23 | 42.07 | 75
Total | [13 empty] | 158.24 | 12.24 | 7.74