## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I | SM/14924 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd/3rd/4th site) and Allied Works for Bansgara ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000126/2022-2023 | 1669/BD-I | 14/03/2023 | 13/04/2023 | JIYARUL SK | 4.19 | 2.35 | 56.07 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I | SM/14924 | Augmentation | Augmentation of Bansgara Zone-I Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000024/2023-2024 | 312/BD-I | 14/06/2023 | 27/05/2026 | MODERN CONSTRUCTION | 281.33 | 112.91 | 40.14 | 30
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I | SM/14924 | Augmentation | Balance and Allied work for Laying Rising Main (DI K-9) and Distribution System (DI-K7) including inter connection with supply of necessary CI special and valve at Head Work Site including road restoration for augmentation work of Bansgrara Zone -I Water Supply Scheme , under Jal Jeevan Mission within Lalgola block under Berhampore DIvision -I , PHE.Dte. in the district of Murshidabad. | Assistant Engineer | JE | ORD/000077/2025-2026 | 844/BD-I | 23/06/2025 | 20/12/2025 | MODERN CONSTRUCTION | 57.56 | 0 | 0 | 80
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I | SM/14924 | Augmentation | Repair And Renovation Works Of OHR (800 Cum) of Ground Water Based Supply Scheme for Basgara Zone-I of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000268/2023-2024 | 990/BD-I | 30/10/2023 | 29/11/2023 | MAA CONSTRUCTION | 10.52 | 9.84 | 93.57 | 90
Total | [13 empty] | 353.6 | 125.11 | 35.38