## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14951 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SADHUKHALI Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000005/2023-2024 | 41/BD-I | 20/04/2023 | 30/04/2023 | TECHVISION | 2.63 | 0 | 0 | 100
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14951 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,ZONE-II of SADHUKHALI ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000076/2023-2024 | 3786/MEDB | 03/11/2023 | 03/02/2024 | SARKAR CONSTRUCTION | 11.37 | 0 | 0 | 7
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14951 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 196/BD-I/26 | 09/02/2024 | 09/02/2024 | Resource Division | 3.7 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14951 | Augmentation | Augmentation of Sadhukhali Zone-II Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant( AIRP ), pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga -II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. [2nd Call for WBPHED/EE/BD-I/NIeT-20 of 2022 ¿ 2023(sl-02)] | Assistant Engineer-II | JE,Junior Engineer-I | ORD/000126/2023-2024 | 845/BD-I | 05/09/2023 | 17/05/2025 | RAJ KUMAR MONDAL | 302.11 | 0 | 0 | 0
Total | [13 empty] | 319.8 | 0 | 0