## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 196/BD-I/27 | 09/02/2024 | 09/02/2024 | Resource Division | 31.44 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | Augmentation | Augmentation of Ramnachandpur zone_IV Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in NAWDA Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-II | JE | ORD/000139/2023-2024 | 622/BD-I | 03/08/2023 | 01/11/2025 | AJAY MONDAL | 277.49 | 0 | 0 | 20
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Ramnachandpur Zone-IV" ground water supply scheme in NAWDA Block,under Berhampore Division-I, P.H.E Dte(Capacity-52.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | Assistant Engineer-II |  | ORD/000033/2024-2025 | 996/BD-I | 20/06/2024 | 20/06/2025 | M/S RUBIET HOSSAIN | 159.77 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | Augmentation | RAMNACHANDRAPUR ZONE-IV to accommodate construction of Boundary Wall under Jal Jivan Mission of NAWDA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000448/2023-2024 | 451/BD-I | 15/03/2024 | 05/09/2025 | PRAVAT KUMAR GHOSH | 21.46 | 0 | 0 | 95
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of RAMNACHANDPUR ZONE-IV Water Supply Scheme under Jal Jevan Mission within Nawda Block under Berhampore Division-I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer-II |  | ORD/000331/2024-2025 | 282/BD-I | 12/02/2025 | 13/04/2025 | MD NAJRUL ISLAM | 7.5 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RAMNACHANDPUR ZONE - IV Water Supply Scheme( 1st & 2nd TW Site) within Nawda Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer-II |  | ORD/000374/2024-2025 | 429/BD-I | 19/03/2025 | 18/04/2025 | GENUINE | 18.02 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of RAMNACHANDPUR ZONE - IV PWSS under Jal Jeevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000010/2025-2026 | 598/BD-I | 22/04/2025 | 21/06/2025 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 19 | 0 | 0 | 0
Total | [13 empty] | 534.67 | 0 | 0