## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . | SM/15228 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 196/BD-I/19 | 09/02/2024 | 09/02/2024 | Resource Division | 18.26 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . | SM/15228 | Augmentation | Augmentation of Bali Zone-III Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-II | JE | ORD/000255/2023-2024 | 972/BD-I | 18/10/2023 | 02/04/2026 | BISWAJYOTI BHATTACHARYYA | 322.8 | 104.56 | 32.39 | 95
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . | SM/15228 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Bali Zone-III" ground water supply scheme in NAWDA Block,under Berhampore Division-I, P.H.E Dte(Capacity-57.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | Assistant Engineer-II |  | ORD/000030/2024-2025 | 993/BD-I | 20/06/2024 | 20/06/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 165.61 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . | SM/15228 | Augmentation | BALI ZONE-III PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of NAWDA Block, Murshidabad District under Berhampore Division-I, PHE.Dte | Assistant Engineer-II | JE | ORD/000447/2023-2024 | 450/BD-I | 15/03/2024 | 16/02/2025 | ANUPA ENTERPRISE | 21.03 | 3.84 | 18.27 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . | SM/15228 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of BALI ZONE-III Water Supply Scheme, under Jal Jevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer-II | JE | ORD/000324/2024-2025 | 271/BD-I | 11/02/2025 | 08/10/2025 | M/S MUKTI CONSTRUCTION | 8.55 | 0 | 0 | 90
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Bali Zone-III pipe water supply scheme . | SM/15228 | Augmentation | NEW SERVICE CONNECTION AT BALI Z3 PH 1 C ID 304565496 |  |  | BILL/00068/2025-2026 | 53/WBSEDCL-3 | 07/08/2025 | 07/08/2025 | WBSEDCL | 6.07 | 0 | 0 | 0
7 | MURSHIDABAD |  | Central Drilling | Augmentation of Bali Zone-III pipe water supply scheme . | SM/15228 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 14.29 | 0.07 | 11
Total | [13 empty] | 21882.07 | 122.69 | 0.56