## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III | SM/15231 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-III under Bansgara ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000147/2023-2024 | 632/MEDB | 02/02/2024 | 02/05/2024 | M/S K.P. PRAMANIK | 22.17 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III | SM/15231 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 201/BD-1/23 | 10/02/2024 | 10/02/2024 | Resource Division | 66.74 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III | SM/15231 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,Assistant Engineer-I | JE,JE_Pravin Kumar Gupta | ORD/000297/2022-2023 | 1742/BD-I | 22/03/2023 | 01/04/2023 | ENVIROTECH SOLUTIONS | 2.55 | 0 | 0 | 95
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III | SM/15231 | Augmentation | Formal work order for Augmentation of Bansgara Zone-III Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000117/2023-2024 | 463/BD-I | 17/07/2023 | 01/01/2026 | SAMBHUNATH ROY | 291.11 | 0 | 0 | 15
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III | SM/15231 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bansgara Zone-III Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000036/2023-2024 | 138/BD-I | 12/05/2023 | 01/02/2025 | HARUN ALL RASHID & BROTHERS | 17.66 | 9.64 | 54.61 | 100
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III | SM/15231 | Augmentation | NEW CONNECTION AT BANSGARA Z-III PH-I |  |  | BILL/00076/2025-2026 | 53/WBSEDCL-5 | 07/08/2025 | 07/08/2025 | WBSEDCL | 5.61 | 0 | 0 | 0
Total | [13 empty] | 405.83 | 9.64 | 2.38