## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. | SM/15232 | Augmentation | Augmentation of Bansgara Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I |  | ORD/000138/2023-2024 | 621/BD-I | 03/08/2023 | 08/06/2024 | BURIMA CONSTRUCTION | 367.54 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. | SM/15232 | Augmentation | BANSGARA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000450/2023-2024 | 453/BD-I | 15/03/2024 | 14/05/2024 | KAUSHIK MAJUMDAR | 21.78 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. | SM/15232 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 201/BD-1/24 | 10/02/2024 | 10/02/2024 | Resource Division | 13.68 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. | SM/15232 | Augmentation | Construction of Pump House Cum Chlorine Room at Head Work Site of BANSGARA ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000016/2025-2026 | 613/BD-I | 22/04/2025 | 06/06/2025 | BIJOY SINGHA | 8.81 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. | SM/15232 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd TW Site of BANSGARA ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000020/2025-2026 | 626/BD-I | 24/04/2025 | 23/06/2025 | SUSHANTA MANDAL | 18.91 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. | SM/15232 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BANSGARA-II PWSS(TW-I&II) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer |  | ORD/000377/2024-2025 | 432/BD-I | 19/03/2025 | 18/04/2025 | SARKAR WATER SUPPLY AGENCY | 18 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. | SM/15232 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000537/2024-2025 | 323/MEDB | 10/02/2025 | 10/05/2025 | ARINDAM MAJUMDAR | 24.68 | 0 | 0 | 0
Total | [13 empty] | 473.42 | 0 | 0