## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 201/BD-1/25 | 10/02/2024 | 10/02/2024 | Resource Division | 139.52 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Bajipur Madhupur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000125/2022-2023 | 1671/BD-I | 14/03/2023 | 13/04/2023 | JAMUNA CONSTRUCTION | 2.85 | 2.82 | 98.84 | 100
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd TW Site of BAJUPUR MADHUPUR ZONE-I PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000380/2024-2025 | 442/BD-I | 20/03/2025 | 19/05/2025 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 19 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | Augmentation | BAJUPUR MADHUPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000449/2023-2024 | 452/BD-I | 15/03/2024 | 01/04/2026 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 21.46 | 9.7 | 45.2 | 30
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bajupur Madhupur Zone - I Water Supply Scheme (TW - I & II Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000365/2024-2025 | 320/BD-I | 24/02/2025 | 11/03/2025 | MERCURY ENGINEERING COMPANY | 18 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | Augmentation | Construction of Pump House Cum Chlorine Room at Head Work Site of BAJUPUR MADHUPUR ZONE -I PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer | JE | ORD/000007/2025-2026 | 594/BD-I | 22/04/2025 | 06/06/2025 | JAKIR HOSSAIN PRAMANIK | 8.66 | 0 | 0 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BAJIPUR MADHUPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000266/2022-2023 | 1689/BD-I | 14/03/2023 | 24/03/2023 | ENVIROTECH SOLUTIONS | 3.14 | 3.17 | 101 | 1
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | Augmentation | Repair And Renovation Works Of OHR (500 Cum) forBajupurMadhupur Zone-I water supply scheme of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000299/2023-2024 | 1067/BD-I | 21/11/2023 | 21/12/2023 | KAUSHIK MAJUMDAR | 9.74 | 7.19 | 73.81 | 80
Total | [13 empty] | 222.38 | 22.88 | 10.29