## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of GAUKHANA ground water based water supply scheme under Block- LALGOLA, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000283/2023-2024 | 3785/MEDB | 03/11/2023 | 03/02/2024 | DAS ENTERPRISE (CHOA) | 11.25 | 9.32 | 82.84 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 201/BD-1/12 | 10/02/2024 | 10/02/2024 | Resource Division | 36.3 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 1510/BD-I/5 | 12/09/2024 | 12/09/2024 | Resource Division | 3.44 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | NEW CONNECTION AT GAUKHANA PH-I |  |  | BILL/00521/2024-2025 | 170/WBSEDCL-JJM | 31/07/2024 | 31/07/2024 | WBSEDCL | 6.98 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | Augmentation of Gaukhana Piped water supply scheme to accommodate construction of OHR ,Arsenic cum Iron Removal Plant( AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000153/2023-2024 | 680/BD-I | 10/08/2023 | 01/01/2026 | ARABINDA GHOSH | 317.21 | 0 | 0 | 50
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | GAUKHANA PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000428/2023-2024 | 328/BD-I | 29/02/2024 | 24/08/2025 | SANTA TRADING | 22.94 | 0 | 0 | 60
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | Improvement of existing AIRP(Gober Danga Model) (Capacity-21.0 Cum/ Hr.) of GAUKHANA Water supply Scheme under Jal Jeevan Mission within Lalgola block under Berhampore Division-I, P.H.E Dte. In the district of Murshidabad. | Assistant Engineer |  | ORD/000068/2025-2026 | 721/BD-I | 14/05/2025 | 13/06/2025 | MS GUNGUN CONSTRUCTION | 20.25 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for GOUKHANA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000258/2022-2023 | 1681/BD-I | 14/03/2023 | 24/03/2023 | ENVIROTECH SOLUTIONS | 2.46 | 2.48 | 101 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Gaukhana ground Water Supply Scheme under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000013/2023-2024 | 60/BD-I | 25/04/2023 | 25/05/2023 | SAIF TRADERS | 2.25 | 2.21 | 98.4 | 100
10 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gaukhana Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer | JE | ORD/000033/2023-2024 | 125/BD-I | 12/05/2023 | 11/06/2023 | HARUN ALL RASHID & BROTHERS | 8.92 | 7.93 | 88.91 | 100
11 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | Augmentation | Repair And Renovation Works Of OHR (90.8 Cum) of Ground Water Based Supply Scheme for Gaukhana of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000265/2023-2024 | 987/BD-I | 30/10/2023 | 29/11/2023 | KAKALI ENTERPRISE | 6.11 | 6.05 | 99.03 | 100
Total | [13 empty] | 438.12 | 28 | 6.39