## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-I under SADHUKHALI ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000073/2023-2024 | 4353/MEDB | 29/12/2023 | 01/01/2025 | C.M. ENTERPRISE | 19.4 | 0 | 0 | 8
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sadhukhali Zone-I Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer |  | ORD/000242/2023-2024 | 939/BD-I | 11/10/2023 | 10/11/2023 | B.R SUPPLIERS | 9 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SADHUKHALI Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000267/2022-2023 | 1690/BD-I | 14/03/2023 | 24/03/2023 | TECHVISION | 2.67 | 2.67 | 99.92 | 100
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | Augmentation | Formal work order for Augmentation of Sadhukhali Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE,Junior Engineer-I | ORD/000183/2022-2023 | 1658/BD-I | 13/03/2023 | 21/11/2025 | NOVELTY CONSTRUCTION | 181.42 | 134.82 | 74.31 | 95
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) forSadhukhali Zone-I water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-II | Junior Engineer-I | ORD/000253/2023-2024 | 1014/BD-I | 31/10/2023 | 30/11/2023 | SUKUMAR ROY | 7.69 | 7.59 | 98.68 | 20
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 46 Cum/hr.) with allied work at Sadhukhali Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer-II |  | ORD/000012/2024-2025 | 911/BD-I | 07/06/2024 | 07/07/2024 | MS BAPPA ENTERPRISE | 17 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | Augmentation | SADHUKHALI ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000455/2023-2024 | 459/BD-I | 15/03/2024 | 09/05/2025 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 22.95 | 0 | 0 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 196/BD-I/21 | 09/02/2024 | 09/02/2024 | Resource Division | 33.74 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | Augmentation | Construction of Boundary wall at 2nd Tube Well Site of SADHUKHALI ZONE -I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000014/2025-2026 | 603/BD-I | 22/04/2025 | 06/06/2025 | BARUN DUTTA | 10.19 | 0 | 0 | 0
Total | [13 empty] | 304.06 | 145.07 | 47.71