## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for ANDULBERIA Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000235/2022-2023 | 1593/BD-I | 28/02/2023 | 10/03/2023 | TECHVISION | 3.15 | 2.92 | 92.65 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 196/BD-I/24 | 09/02/2024 | 09/02/2024 | Resource Division | 46.35 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | Augmentation | Augmentation of Andulberia Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-II | JE,Junior Engineer-I | ORD/000211/2022-2023 | 1821/BD-I | 31/03/2023 | 01/01/2026 | KAMIRUL SK AND CO. | 399.58 | 125.59 | 31.43 | 70
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of ANDULBERIA ZONE-II" ground water supply scheme in BELDANGA-II Block under Berhampore Division-I, P.H.E Dte(Capacity-72.00 Cum/hr.) Type-1: Fully Gravity System with RG Filter | Assistant Engineer-II |  | ORD/000031/2024-2025 | 994/BD-I | 20/06/2024 | 20/06/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 197.4 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDULBERIA ZONE - II Water Supply Scheme(3rd TW Site) within Beldanga - II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer-II |  | ORD/000297/2024-2025 | 103/BD-I | 20/01/2025 | 04/02/2025 | HARUN ALL RASHID & BROTHERS | 8.95 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of ANDULBERIA ZONE-II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II | JE | ORD/000042/2025-2026 | 724/BD-I | 15/05/2025 | 12/09/2025 | M/S. MONDAL ENTERPRISE | 19 | 0 | 0 | 100
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | Augmentation | ANDULBERIA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000047/2024-2025 | 1109/BD-I | 10/07/2024 | 06/01/2025 | SARODA CONSTRUCTION & CO | 22.74 | 5.79 | 25.45 | 100
Total | [13 empty] | 697.16 | 134.29 | 19.26