## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | BELIA SYAMPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000092/2023-2024 | 214/BD-I | 17/05/2023 | 30/07/2026 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 40.8 | 13.26 | 32.5 | 50
2 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | BELIA SYAMPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I |  | ORD/000132/2023-2024 | 611/BD-I | 02/08/2023 | 29/01/2024 | ROY CONSTRUCTION (AVIJIT ROY) | 69 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 61/BD-1/17 | 27/04/2023 | 27/04/2023 | Resource Division | 11.74 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Berhampore, Bhagawangola I and II, Domkal, Samserganj, Suti I and II block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000051/2025-2026 | 45/2/MEDB | 29/05/2025 | 29/08/2025 | M/S SAJAHAN CHOWDHURY | 21.32 | 0 | 0 | 0
5 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Belia Shyampur Pipe Water Supply Scheme Block - Bhagwangola-I District - Murshidabad Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000534/2024-2025 | 320/MEDB | 10/02/2025 | 10/05/2025 | SUNIL RABIDAS | 21.38 | 0 | 0 | 0
6 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BELIA SHYAMPUR and Adjoining Mouzas PWSS (TW-I & II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (02 Nos TW) | Assistant Engineer-I |  | ORD/000082/2025-2026 | 849/BD-I | 23/06/2025 | 23/07/2025 | JOY GURU ENTERPRISE | 17.75 | 0 | 0 | 0
7 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | NEW CONNECTION AT BELIA SHYAMPUR PH-I |  |  | BILL/01456/2024-2025 | 426/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 3.97 | 0 | 0 | 0
Total | [13 empty] | 185.95 | 13.26 | 7.13