## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS | SM/16015 | New | MAHISHASTHALI PWSS to accommodate FHTC, Laying Distribution System, under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | Junior Engineer-I | ORD/000047/2023-2024 | 143/BD-I | 15/05/2023 | 30/09/2026 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 96.62 | 0 | 0 | 40
2 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS | SM/16015 | New | MAHISHASTHALI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000106/2023-2024 | 211/BD-I | 17/05/2023 | 30/07/2026 | MANAB KUMAR GHOSH | 38.89 | 12.99 | 33.4 | 75
3 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | MAHISHASTHALI AND ADJOINING MOUJAS PWSS | SM/16015 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Mahishasthali ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000656/2023-2024 | 3691/MEDB | 03/11/2023 | 03/02/2024 | GOENKA ENTERPRISE | 20.9 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS | SM/16015 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 61/BD-1/21 | 27/04/2023 | 27/04/2023 | Resource Division | 15.38 | 0 | 0 | 0
5 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS | SM/16015 | New | MAHISHASTHALI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 350 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I | Junior Engineer-I | ORD/000374/2023-2024 | 116/BD-I | 30/01/2024 | 11/10/2025 | RANADHIR SINHA | 268.39 | 0 | 0 | 30
6 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS | SM/16015 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHISASTHALI and Adjoining Mouzas PWSS (TW-I & II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (02 Nos TW) | Assistant Engineer-I |  | ORD/000080/2025-2026 | 847/BD-I | 23/06/2025 | 23/07/2025 | WATER TECH | 17.75 | 0 | 0 | 0
Total | [13 empty] | 457.93 | 12.99 | 2.84