## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Mechanical | GAYSEPUR PIPED WATER SUPPLY SCHEME | SM/16018 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Gaysepur ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000651/2023-2024 | 3661/MEDB | 03/11/2023 | 03/02/2024 | DAS ENTERPRISE ( MANGO LANE) | 20.87 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | GAYSEPUR PIPED WATER SUPPLY SCHEME | SM/16018 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 61/BD-1/15 | 27/04/2023 | 27/04/2023 | Resource Division | 6.62 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Division I | GAYSEPUR PIPED WATER SUPPLY SCHEME | SM/16018 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 304/BD-1/7 | 22/02/2024 | 22/02/2024 | Resource Division | 3.02 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Division I | GAYSEPUR PIPED WATER SUPPLY SCHEME | SM/16018 | New | GAYESPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000048/2023-2024 | 144/BD-I | 15/05/2023 | 01/08/2025 | SAPTADIP CONSTRUCTION | 58.85 | 0 | 0 | 30
5 | MURSHIDABAD | Lalgola | Berhampore Division I | GAYSEPUR PIPED WATER SUPPLY SCHEME | SM/16018 | New | GAYESPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000343/2023-2024 | 1257/BD-I | 22/12/2023 | 18/06/2025 | M/S HUMAYUN BISWAS | 39.06 | 0 | 0 | 60
6 | MURSHIDABAD | Lalgola | Central Drilling | GAYSEPUR PIPED WATER SUPPLY SCHEME | SM/16018 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 7.05 | 1.54 | 10
Total | [13 empty] | 587.12 | 7.05 | 1.2