## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Beldanga-I | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - MOHESPUR , BLOCK BELDANGA -I ,DISTRICT - MURSHIDABAD. | SM/16050 | New | Mini Piped Water Supply Scheme for Mohespur under Beldanga -I block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-II |  | ORD/000062/2023-2024 | 159/BD-I | 15/05/2023 | 13/08/2023 | TITLI ENTERPRISE | 27.81 | 0 | 0 | 0
2 | MURSHIDABAD | Beldanga-I | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - MOHESPUR , BLOCK BELDANGA -I ,DISTRICT - MURSHIDABAD. | SM/16050 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Mohespur village, Block:- Beldanga-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000217/2023-2024 | 3079/MEDB | 02/08/2023 | 02/11/2023 | DIPALI CONSTRUCTION | 6.12 | 0 | 0 | 0
Total | [13 empty] | 33.92 | 0 | 0