## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 61/BD-1/35 | 27/04/2023 | 27/04/2023 | Resource Division | 13.43 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 304/BD-1/8 | 22/02/2024 | 22/02/2024 | Resource Division | 9.83 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Mechanical | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | New | AMARKUNDU PH-1 |  |  | BILL/01514/2023-2024 | 398/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 9.75 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | New | AMARKUNDA PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer | JE | ORD/000293/2022-2023 | 1825/BD-I | 31/03/2023 | 27/09/2023 | AJOY GHOSH | 96.88 | 58.27 | 60.15 | 20
5 | MURSHIDABAD | Lalgola | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | New | AMARKUNDA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE,Junior Engineer-I | ORD/000086/2023-2024 | 206/BD-I | 17/05/2023 | 30/05/2025 | G M ENTERPRISE | 53.43 | 27.52 | 51.51 | 20
6 | MURSHIDABAD | Lalgola | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | New | AMARKUNDA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART -A) | Assistant Engineer | JE | ORD/000027/2023-2024 | 94/BD-I | 04/05/2023 | 01/04/2026 | TANUSHREE ENTERPRISE | 240.28 | 89.12 | 37.09 | 100
7 | MURSHIDABAD | Lalgola | Central Drilling | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 17 | 2.36 | 20
8 | MURSHIDABAD | Lalgola | Central Drilling | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 6.83 | 1.49 | 10
Total | [13 empty] | 1602.54 | 198.74 | 12.4