## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16266 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 61/BD-1/18 | 27/04/2023 | 27/04/2023 | Resource Division | 11.87 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-II | Berhampore Mechanical | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16266 | New | NEW CONNECTION AT KHAGJANA PH-I |  |  | BILL/00248/2024-2025 | 105/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 4.03 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-II | Berhampore Mechanical | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16266 | New | NEW CONNECTION AT KHAGJANA PH-II |  |  | BILL/01138/2024-2025 |  | 26/11/2024 | 26/11/2024 | WBSEDCL | 4.29 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16266 | New | KHAGJANA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000100/2023-2024 | 218/BD-I | 17/05/2023 | 05/02/2025 | S.K ENTERPRISE (RANITALA) | 53.17 | 0 | 0 | 65
5 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16266 | New | KHAGJANA PWSS to accommodate FHTC, Laying Distribution System,, under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000040/2023-2024 | 118/BD-I | 11/05/2023 | 07/11/2023 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 96.97 | 0 | 0 | 50
6 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16266 | New | Allied work of Laying of Distribution system for the work of Khagjana PWSS to accommodate FHTC, OHR, Laying distribution system, Rising Main under Jal Jeevan Mission of Bhagwangola- II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (Part-A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000165/2024-2025 | 1684/BD-I | 28/10/2024 | 01/04/2025 | S.K ENTERPRISE (RANITALA) | 68.11 | 0 | 0 | 96
7 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16266 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAGJANA and Adjoining Mouzas PWSS (TW - II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division - I, P.H.Engineering Dte. (01 No TW). | Assistant Engineer-I |  | ORD/000047/2025-2026 | 754/BD-I | 22/05/2025 | 06/06/2025 | AJOY GHOSH | 9.01 | 0 | 0 | 0
Total | [13 empty] | 247.45 | 0 | 0