## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 61/BD-1/4 | 27/04/2023 |  | Resource Division | 9.47 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | PURBA KASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I |  | ORD/000088/2023-2024 | 210/BD-I | 17/05/2023 | 15/08/2023 | MARUTI CONSTRUCTION & CO. | 53.43 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | PURBA KASHIPUR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | Junior Engineer | ORD/000292/2022-2023 | 1823/BD-I | 31/03/2023 | 27/09/2023 | MARUTI CONSTRUCTION & CO. | 112.84 | 0 | 0 | 25
4 | MURSHIDABAD | Bhagawangola - I | Berhampore Mechanical | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | NEW CONNECTION AT PURBA KASHIPUR PH-I |  |  | BILL/00242/2024-2025 | 104/WBSEDCL-JJM | 05/06/2024 |  | WBSEDCL | 5.84 | 0 | 0 | 0
5 | MURSHIDABAD | Bhagawangola - I | Berhampore Mechanical | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | NEW CONNECTION AT PURBA KASHIPUR PH-I |  |  | BILL/00242/2024-2025 | 104/WBSEDCL-JJM | 05/06/2024 |  | WBSEDCL | 5.84 | 0 | 0 | 0
6 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Balance work of distribution pipe line under Jal Jeevan Mission for Purba Kashipur Piped Water Supply scheme under Berhampore Division - I , P.H.Engg Dte. In the district of Murshidabad. | Assistant Engineer-I | Junior Engineer | ORD/000069/2024-2025 | 1207/BD-I | 26/07/2024 | 24/09/2024 | MARUTI CONSTRUCTION & CO. | 42.9 | 0 | 0 | 0
7 | MURSHIDABAD | Bhagawangola - I | Central Drilling | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 08/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 0 | 10
8 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | PURBA KASHIPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | Assistant Engineer-I | JE,Junior Engineer | ORD/000116/2023-2024 | 407/BD-I | 06/07/2023 | 05/07/2024 | SANKAR KUMAR BISWAS | 290.34 | 35.85 | 12.35 | 40
Total | [13 empty] | 1240.9 | 35.85 | 2.89