## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 61/BD-1/4 | 27/04/2023 | 27/04/2023 | Resource Division | 9.47 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | NEW CONNECTION AT PURBA KASHIPUR PH-I |  |  | BILL/00242/2024-2025 | 104/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 5.84 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Purba Kasipur and adjoining mouzas piped Water Supply Scheme Dist- Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000019/2025-2026 | 1145/MEDB | 14/05/2025 | 14/08/2025 | MONI ELECTRICAL WORKS | 22.95 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | PURBA KASHIPUR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | Junior Engineer | ORD/000292/2022-2023 | 1823/BD-I | 31/03/2023 | 27/09/2023 | MARUTI CONSTRUCTION & CO. | 112.84 | 0 | 0 | 85
5 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | PURBA KASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer | ORD/000088/2023-2024 | 210/BD-I | 17/05/2023 | 07/11/2025 | MARUTI CONSTRUCTION & CO. | 53.43 | 0 | 0 | 70
6 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | PURBA KASHIPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | Assistant Engineer-I | JE,Junior Engineer | ORD/000116/2023-2024 | 407/BD-I | 06/07/2023 | 01/04/2026 | SANKAR KUMAR BISWAS | 290.34 | 0 | 0 | 40
7 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Balance work of distribution pipe line under Jal Jeevan Mission for Purba Kashipur Piped Water Supply scheme under Berhampore Division - I , P.H.Engg Dte. In the district of Murshidabad. | Assistant Engineer-I | Junior Engineer | ORD/000069/2024-2025 | 1207/BD-I | 26/07/2024 | 24/09/2024 | MARUTI CONSTRUCTION & CO. | 42.9 | 0 | 0 | 85
8 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Construction Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of PURBA KASHIPUR PWSS under Jal Jeevan Mission within Bhagwangola-I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-I |  | ORD/000019/2025-2026 | 625/BD-I | 24/04/2025 | 23/06/2025 | SHIV SHAKTI CONSTRUCTION | 18.82 | 0 | 0 | 80
Total | [13 empty] | 556.59 | 0 | 0