## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 61/BD-1/4 | 27/04/2023 | 27/04/2023 | Resource Division | 9.47 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | NEW CONNECTION AT PURBA KASHIPUR PH-I |  |  | BILL/00242/2024-2025 | 104/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 5.84 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Purba Kasipur and adjoining mouzas piped Water Supply Scheme Dist- Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000019/2025-2026 | 1145/MEDB | 14/05/2025 | 14/08/2025 | MONI ELECTRICAL WORKS | 22.95 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | PURBA KASHIPUR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | Junior Engineer | ORD/000292/2022-2023 | 1823/BD-I | 31/03/2023 | 27/09/2023 | MARUTI CONSTRUCTION & CO. | 112.84 | 49.88 | 44.21 | 85
5 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | PURBA KASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer | ORD/000088/2023-2024 | 210/BD-I | 17/05/2023 | 07/11/2025 | MARUTI CONSTRUCTION & CO. | 53.43 | 0 | 0 | 70
6 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | PURBA KASHIPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | Assistant Engineer-I | JE,Junior Engineer | ORD/000116/2023-2024 | 407/BD-I | 06/07/2023 | 01/04/2026 | SANKAR KUMAR BISWAS | 290.34 | 105.33 | 36.28 | 40
7 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Balance work of distribution pipe line under Jal Jeevan Mission for Purba Kashipur Piped Water Supply scheme under Berhampore Division - I , P.H.Engg Dte. In the district of Murshidabad. | Assistant Engineer-I | Junior Engineer | ORD/000069/2024-2025 | 1207/BD-I | 26/07/2024 | 24/09/2024 | MARUTI CONSTRUCTION & CO. | 42.9 | 0 | 0 | 85
8 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Construction Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of PURBA KASHIPUR PWSS under Jal Jeevan Mission within Bhagwangola-I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-I |  | ORD/000019/2025-2026 | 625/BD-I | 24/04/2025 | 23/06/2025 | SHIV SHAKTI CONSTRUCTION | 18.82 | 0 | 0 | 80
9 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PURBA KASHIPUR Water Supply Scheme(2nd TW site) within Bhagwangola-I Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer-I | Junior Engineer | ORD/000296/2024-2025 | 102/BD-I | 20/01/2025 | 20/07/2025 | HARUN ALL RASHID & BROTHERS | 8.93 | 0 | 0 | 100
Total | [13 empty] | 565.52 | 155.21 | 27.45