## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | Augmentation of Koasbagoas Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), pump house and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000023/2023-2024 | 375/BD-I | 28/06/2023 | 27/06/2025 | MAMATA USHA ENTERPRISE | 534.97 | 287.74 | 53.79 | 75
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under KOASBAGOAS ground water based water supply scheme under Block_ Raninagar-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000059/2023-2024 | 3762/MEDB | 03/11/2023 | 03/02/2024 | A.G. ENTERPRISE | 35.21 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASBAGOAS Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000269/2022-2023 | 1692/BD-I | 14/03/2023 | 24/03/2023 | RADIANT | 2.67 | 2.67 | 100 | 100
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) of Ground Water Based Supply Scheme for Kasbagoas of Raninagar-I block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | JE | ORD/000261/2023-2024 | 1030/BD-I | 01/11/2023 | 01/12/2023 | M/S. MONDAL ENTERPRISE 12/6/1, OLD POLICE LINE ROAD, GORABAZAR | 8.01 | 6.3 | 78.61 | 100
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kasbagoas Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte.(For 3 nos. Tubewell) | Assistant Engineer | JE | ORD/000316/2023-2024 | 1146/BD-I | 04/12/2023 | 03/01/2024 | MAMATA USHA ENTERPRISE | 34.71 | 29.87 | 86.07 | 100
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 194/BD-I/3 | 09/02/2024 | 09/02/2024 | Resource Division | 55.6 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | Meter shifting kasba goas pwss |  |  | BILL/01596/2023-2024 | 416/WBSEDCL-JJM | 06/03/2024 | 06/03/2024 | WBSEDCL | 0.28 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | NEW CONNECTION KASBAGOAS Z-I PH-I |  |  | BILL/01629/2023-2024 | 480/WBSEDCL-JJM | 21/03/2024 | 21/03/2024 | WBSEDCL | 10.02 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | NEW CONNECTION KASBAGOAS Z-I PH-II |  |  | BILL/01627/2023-2024 | 479/WBSEDCL-JJM | 21/03/2024 | 21/03/2024 | WBSEDCL | 3.43 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of KASBAGOAS ZONE-II PWSS under Jal Jeevan Mission within Raninagar -I Block under Berhampore Division-I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000083/2025-2026 | 875/BD-I | 01/07/2025 | 30/08/2025 | TAIMUR SK | 16.51 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | Augmentation | Construction Pump House Cum Chlorine Room at KASBAGOAS Water Supply Scheme under Jal Jevan Mission within Raninagar-I Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer |  | ORD/000325/2024-2025 | 272/BD-I | 11/02/2025 | 12/04/2025 | TAIMUR SK | 7.5 | 0 | 0 | 0
Total | [13 empty] | 708.9 | 326.58 | 46.07