## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | New | SYAMPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE,Junior Engineer | ORD/000104/2023-2024 | 222/BD-I | 17/05/2023 | 14/02/2025 | SKY CONSTRUCTION | 50.19 | 28.32 | 56.43 | 40
2 | MURSHIDABAD | Lalgola | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | New | SYAMPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE,Junior Engineer | ORD/000171/2023-2024 | 663/BD-I | 09/08/2023 | 01/10/2026 | M/S ABDUL MATIN | 290.59 | 115.52 | 39.76 | 30
3 | MURSHIDABAD | Lalgola | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 61/BD-1/19 | 27/04/2023 | 27/04/2023 | Resource Division | 15.51 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Central Drilling | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 12.96 | 1.8 | 20
5 | MURSHIDABAD | Lalgola | Central Drilling | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 0 | 10
6 | MURSHIDABAD | Lalgola | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 304/BD-1/5 | 22/02/2024 | 22/02/2024 | Resource Division | 7.38 | 0 | 0 | 0
7 | MURSHIDABAD | Lalgola | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | New | SHYAMPUR PH-1 |  |  | BILL/01519/2023-2024 | 397/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 6.46 | 0 | 0 | 0
8 | MURSHIDABAD | Lalgola | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under SYAMPUR ground water based water supply scheme under Block_ LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000025/2025-2026 | 1154/MEDB | 14/05/2025 | 14/08/2025 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 10.92 | 0 | 0 | 0
9 | MURSHIDABAD | Lalgola | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SHYAMPUR PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | Assistant Engineer | Junior Engineer | ORD/000071/2025-2026 | 838/BD-I | 23/06/2025 | 08/07/2025 | B.M. ENGINEERING & CONSTRUCTION | 9 | 0 | 0 | 0
Total | [13 empty] | 1568.97 | 156.8 | 9.99