## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | KATALIA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE,Junior Engineer | ORD/000103/2023-2024 | 221/BD-I | 17/05/2023 | 28/09/2025 | NURUL HASAN BISWAS | 52.76 | 0 | 0 | 66
2 | MURSHIDABAD | Berhampore | Central Drilling | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 11.68 | 0.05 | 11
3 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | KATALIA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE,Junior Engineer | ORD/000160/2023-2024 | 685/BD-I | 10/08/2023 | 27/08/2026 | C.X.CONSTRUCTION & CO. | 259.02 | 13.63 | 5.26 | 75
4 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 61/BD-1/20 | 27/04/2023 | 27/04/2023 | Resource Division | 15.38 | 0 | 0 | 0
5 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Katalia" ground water supply scheme in Berhampore Block, under Berhampore Division-I, P.H.E Dte. (Capacity-36 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | Assistant Engineer-II | Junior Engineer | ORD/000037/2024-2025 | 1000/BD-I | 20/06/2024 | 20/06/2025 | ACQUA CONSTRUCTION CONSORTIUM | 147.9 | 0 | 0 | 0
6 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 2096/BD-I/7 | 25/11/2024 | 25/11/2024 | Resource Division | 8.46 | 0 | 0 | 0
7 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATALIA Water Supply Scheme(TW-II) within Berhampore Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer-II | Junior Engineer | ORD/000283/2024-2025 | 15/BD-I | 06/01/2025 | 01/04/2025 | SARKAR WATER SUPPLY AGENCY | 9 | 0 | 0 | 100
8 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Bored Cast-in-situ_ M30 _ grade 500 mm dia. R.C.C. pile for Construction of OHR at Head Work site of KATALIA Ground Piped Water Supply Scheme under Jal Jeevan Mission within Berhampore Block under Berhampore Division-I, PHE.Dte. in the district of Murshidabad. | Assistant Engineer-II | Junior Engineer | ORD/000329/2024-2025 | 278/BD-I | 12/02/2025 | 11/05/2025 | C.X.CONSTRUCTION & CO. | 30.71 | 0 | 0 | 100
9 | MURSHIDABAD | Berhampore | Berhampore Mechanical | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | NEW CONNECTION AT KANTHALIYA PH-I |  |  | BILL/01452/2024-2025 | 420/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 8.3 | 0 | 0 | 0
Total | [13 empty] | 21871.29 | 25.31 | 0.12