## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 61/BD-1/20 | 27/04/2023 | 27/04/2023 | Resource Division | 15.38 | 0 | 0 | 0
2 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 2096/BD-I/7 | 25/11/2024 | 25/11/2024 | Resource Division | 8.46 | 0 | 0 | 0
3 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | KATALIA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE,Junior Engineer | ORD/000103/2023-2024 | 221/BD-I | 17/05/2023 | 28/09/2025 | NURUL HASAN BISWAS | 52.76 | 0 | 0 | 66
4 | MURSHIDABAD | Berhampore | Central Drilling | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | KATALIA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE,Junior Engineer | ORD/000160/2023-2024 | 685/BD-I | 10/08/2023 | 27/12/2025 | C.X.CONSTRUCTION & CO. | 259.02 | 0 | 0 | 30
6 | MURSHIDABAD | Berhampore | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Katalia" ground water supply scheme in Berhampore Block, under Berhampore Division-I, P.H.E Dte. (Capacity-36 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | Assistant Engineer-II |  | ORD/000037/2024-2025 | 1000/BD-I | 20/06/2024 | 20/06/2025 | ACQUA CONSTRUCTION CONSORTIUM | 147.9 | 0 | 0 | 0
Total | [13 empty] | 21823.28 | 0 | 0