## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Beldanga-II | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 61/BD-1/16 | 27/04/2023 | 27/04/2023 | Resource Division | 12.25 | 0 | 0 | 0
2 | MURSHIDABAD | Beldanga-II | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 2096/BD-I/2 | 25/11/2024 | 25/11/2024 | Resource Division | 5.01 | 0 | 0 | 0
3 | MURSHIDABAD | Beldanga-II | Berhampore Mechanical | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | NEW CONNECTION AT HARIGANJ PH-I |  |  | BILL/00614/2024-2025 | 184/WBSEDCL-JJM | 09/08/2024 | 09/08/2024 | WBSEDCL | 5.15 | 0 | 0 | 0
4 | MURSHIDABAD | Beldanga-II | Berhampore Mechanical | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under HARIGANJA ground water based water supply scheme under Block_LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000023/2025-2026 | 1152/MEDB | 14/05/2025 | 14/08/2025 | ASSOCIATED ELECTRICAL CO. | 10.83 | 0 | 0 | 0
5 | MURSHIDABAD | Beldanga-II | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | HARIGANJA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000043/2023-2024 | 74/BD-I | 28/04/2023 | 27/04/2025 | M/S SAJEDA ENTERPRISE | 141.8 | 26.5 | 18.69 | 65
6 | MURSHIDABAD | Beldanga-II | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Hariganja" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-30 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000029/2024-2025 | 992/BD-I | 20/06/2024 | 20/06/2026 | NATIONAL CONSTRUCTION | 142.73 | 0 | 0 | 5
7 | MURSHIDABAD | Beldanga-II | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at HARIGANJ PWSS (H/W Site) under Jal Jeevan Mission in Beldanga-II Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | Assistant Engineer-II |  | ORD/000381/2024-2025 | 443/BD-I | 20/03/2025 | 04/04/2025 | M/S S. DAS & ENTERPRISE | 9 | 0 | 0 | 0
Total | [13 empty] | 326.76 | 26.5 | 8.11