## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Beldanga - II | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 61/BD-1/16 | 27/04/2023 |  | Resource Division | 12.25 | 0 | 0 | 0
2 | MURSHIDABAD | Beldanga - II | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | HARIGANJA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000043/2023-2024 | 74/BD-I | 28/04/2023 | 27/04/2024 | M/S SAJEDA ENTERPRISE | 141.8 | 0 | 0 | 15
3 | MURSHIDABAD | Beldanga - II | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | HARIGANJA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000284/2023-2024 | 1001/BD-I | 31/10/2023 | 29/01/2024 | SUSHANTA MANDAL | 39.1 | 0 | 0 | 31
4 | MURSHIDABAD | Beldanga - II | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Hariganja" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-30 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | Assistant Engineer-II |  | ORD/000029/2024-2025 | 992/BD-I | 20/06/2024 | 15/06/2025 | NATIONAL CONSTRUCTION | 142.73 | 0 | 0 | 0
5 | MURSHIDABAD | Beldanga - II | Berhampore Mechanical | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | NEW CONNECTION AT HARIGANJ PH-I |  |  | BILL/00614/2024-2025 | null | 02/08/2024 |  | WBSEDCL | 5.15 | 0 | 0 | 0
6 | MURSHIDABAD | Beldanga - II | Central Drilling | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21680.78 | 0 | 0