## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 201/BD-1/19 | 10/02/2024 | 10/02/2024 | Resource Division | 23.75 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 1510/BD-I/13 | 12/09/2024 | 12/09/2024 | Resource Division | 7.2 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | NEW CONNECTION MAIYA PH-1 |  |  | BILL/01512/2023-2024 | 396/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 9.31 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of Maia Zone - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000012/2025-2026 | 599/BD-I | 22/04/2025 | 21/06/2025 | SUJAUDDIN SHAIKH | 18.99 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of Maia Zone-II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000379/2024-2025 | 441/BD-I | 20/03/2025 | 19/05/2025 | SHIBAM ENTERPRISE | 19 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MAIA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000006/2023-2024 | 47/BD-I | 25/04/2023 | 05/05/2023 | ENVIROTECH SOLUTIONS | 2.49 | 2.49 | 100 | 100
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | MAYA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000453/2023-2024 | 456/BD-I | 15/03/2024 | 09/05/2025 | DHRITIPALI | 21.91 | 0 | 0 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of Maia Zone -II Water Supply Scheme , under Jal Jevan Mission of Lalgola Block of Murshidabad District under Berhampore Division -I, PHE.Dte. | Assistant Engineer | JE | ORD/000275/2024-2025 | 07/BD-I | 06/01/2025 | 20/02/2025 | BARUN DUTTA | 8.11 | 0 | 0 | 90
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | NEW CONNECTION AT MAYA Z-II P-II |  |  | BILL/01458/2024-2025 | 425/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 4.01 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | Augmentation of Maia Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer | JE | ORD/000127/2023-2024 | 540/BD-I | 28/07/2023 | 27/12/2026 | MD SAJAHAN ALI | 364.59 | 117.99 | 32.36 | 35
11 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.72 | 2.04 | 20
12 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 13.29 | 2.9 | 10
Total | [13 empty] | 1658.28 | 148.48 | 8.95