## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Murshidabad Jiaganj | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Chandabag, Block- Murshidabad-Jiagunj, District- Murshidabad. | SM/16435 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chandabag village, Block:- Murshidabad - Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000174/2023-2024 | 3035 | 02/08/2023 | 02/11/2023 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0 | 0
2 | MURSHIDABAD | Murshidabad Jiaganj | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Chandabag, Block- Murshidabad-Jiagunj, District- Murshidabad. | SM/16435 | New | Mini Piped Water Supply Scheme for Chandabag under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I |  | ORD/000065/2023-2024 | 162/BD-I | 16/05/2023 | 14/08/2023 | PRAVAT KUMAR GHOSH | 24.63 | 0 | 0 | 0
Total | [13 empty] | 30.95 | 0 | 0