## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Nawda | Berhampore Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Sibnagar Zone IV, Block- Nawda, District- Murshidabad. | SM/16437 | New | Mini Piped Water Supply Scheme for Sibnagar Zone-IV under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-II |  | ORD/000060/2023-2024 | 157/BD-I | 15/05/2023 | 13/08/2023 | GANGULY ENTERPRISE | 30.54 | 0 | 0 | 0
2 | MURSHIDABAD | Nawda | Berhampore Mechanical | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Sibnagar Zone IV, Block- Nawda, District- Murshidabad. | SM/16437 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-IV village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000185/2023-2024 | 3046/MEDB | 02/08/2023 | 31/10/2023 | TARUN KUMAR BHATTACHARYA | 6.26 | 0 | 0 | 0
Total | [13 empty] | 36.8 | 0 | 0