## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Berhampore | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 61/BD-1/6 | 27/04/2023 | 27/04/2023 | Resource Division | 15.38 | 0 | 0 | 0
2 | MURSHIDABAD | Berhampore | Berhampore Mechanical | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SAMSASKAR ground water based water supply scheme under Block_ Berhampore Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000701/2023-2024 | 4339/MEDB | 29/12/2023 | 29/03/2024 | DEBJYOTI BASU | 20.87 | 0 | 0 | 10
3 | MURSHIDABAD | Berhampore | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 2096/BD-I/4 | 25/11/2024 | 25/11/2024 | Resource Division | 10 | 0 | 0 | 0
4 | MURSHIDABAD | Berhampore | Berhampore Mechanical | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | NEW CONNECTION SAMASKAR PH-I |  |  | BILL/01657/2023-2024 | 10/WBSEDCL-JJM | 09/04/2024 | 09/04/2024 | WBSEDCL | 7.19 | 0 | 0 | 0
5 | MURSHIDABAD | Berhampore | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | SAMASKAR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-II | JE,Junior Engineer | ORD/000294/2022-2023 | 1824/BD-I | 31/03/2023 | 29/09/2025 | ARINDAM MAJUMDAR | 109.77 | 0 | 0 | 35
6 | MURSHIDABAD | Berhampore | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | SAMASKAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE,Junior Engineer | ORD/000102/2023-2024 | 220/BD-I | 17/05/2023 | 01/01/2026 | BINAPANI ENTERPRISE | 52.7 | 16.88 | 32.03 | 5
7 | MURSHIDABAD | Berhampore | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAMASKAR Water Supply Scheme(TW - II) within Berhampore Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-II | Junior Engineer | ORD/000276/2024-2025 | 08/BD-I | 06/01/2025 | 03/09/2025 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0 | 100
Total | [13 empty] | 224.93 | 16.88 | 7.5