## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS | SM/16780 | New | BHAGWANGOLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I |  | ORD/000091/2023-2024 | 213/BD-I | 17/05/2023 | 15/08/2023 | ARJIMA CONSTRUCTION | 39.48 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS | SM/16780 | New | BHAGWANGOLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 450 cum) under Jal Jivan Mission of BHAGWANGOLA -I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I |  | ORD/000269/2023-2024 | 974/BD-I | 18/10/2023 | 24/07/2024 | GIRIDHARI SAHA | 359.56 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS | SM/16780 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 61/BD-1/27 | 27/04/2023 | 27/04/2023 | Resource Division | 13.43 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | BHAGWANGOLA AND ADJOING MOUJAS PWSS | SM/16780 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHAGWANGOLA , BLOCK - BHAGWANGOLA -I , DISTRICT - MURSHIDABAD. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000029/2025-2026 | 1181/MEDB | 16/05/2025 | 16/08/2025 | M/S K.P. PRAMANIK | 23.66 | 0 | 0 | 0
5 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS | SM/16780 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BHAGWANGOLA PWSS(TW-I&II) under Jal Jeevan Mission in Bhagwangola-I Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer-I |  | ORD/000018/2025-2026 | 617/BD-I | 23/04/2025 | 23/05/2025 | JOY HIND TUBEWELLS | 17.99 | 0 | 0 | 0
6 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS | SM/16780 | New | Construction Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of BHAGWANGOLA PWSS under Jal Jeevan Mission within Bhagwangola-I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000006/2025-2026 | 593/BD-I | 22/04/2025 | 19/10/2025 | AMAN CONSTRUCTION | 15.2 | 0 | 0 | 82
Total | [13 empty] | 469.33 | 0 | 0