## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Beldanga-II | Central Drilling | SHUKUR PUKUR PWSS | SM/16782 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 11.48 | 0.05 | 11
2 | MURSHIDABAD | Beldanga-II | Berhampore Division I | SHUKUR PUKUR PWSS | SM/16782 | New | SHUKUR PUKUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000087/2023-2024 | 207/BD-I | 17/05/2023 | 28/09/2025 | ABIDA CONSTRUCTION | 40.82 | 0 | 0 | 51
3 | MURSHIDABAD | Beldanga-II | Berhampore Division I | SHUKUR PUKUR PWSS | SM/16782 | New | SHUKUR PUKUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000133/2023-2024 | 612/BD-I | 02/08/2023 | 26/12/2025 | NOVELTY CONSTRUCTION | 52.15 | 14.56 | 27.92 | 76
4 | MURSHIDABAD | Beldanga-II | Berhampore Division I | SHUKUR PUKUR PWSS | SM/16782 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 61/BD-1/34 | 27/04/2023 | 27/04/2023 | Resource Division | 8.65 | 0 | 0 | 0
5 | MURSHIDABAD | Beldanga-II | Berhampore Division I | SHUKUR PUKUR PWSS | SM/16782 | New | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 2096/BD-I/5 | 25/11/2024 | 25/11/2024 | Resource Division | 3.7 | 0 | 0 | 0
6 | MURSHIDABAD | Beldanga-II | Berhampore Mechanical | SHUKUR PUKUR PWSS | SM/16782 | New | NEW CONNECTION AT SUKURPUKUR PH-1 |  |  | BILL/00616/2024-2025 | 183/WBSEDCL-JJM | 09/08/2024 | 09/08/2024 | WBSEDCL | 10.55 | 0 | 0 | 0
7 | MURSHIDABAD | Beldanga-II | Berhampore Division I | SHUKUR PUKUR PWSS | SM/16782 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SUKURPUKUR Water Supply Scheme(2nd TW Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000323/2024-2025 | 262/BD-I | 07/02/2025 | 09/08/2025 | SINGHA AND CO. | 9 | 0 | 0 | 100
Total | [13 empty] | 21464.63 | 26.04 | 0.12