## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 61/BD-1/33 | 27/04/2023 | 27/04/2023 | Resource Division | 13.12 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | PURBA GOBINDAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 200 cum) under Jal Jivan Mission of BHAGWANGOLA -II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000246/2023-2024 | 967/BD-I | 17/10/2023 | 03/02/2026 | SAMBHUNATH ROY | 298.57 | 96.39 | 32.28 | 35
3 | MURSHIDABAD | Bhagawangola-II | Berhampore Mechanical | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | NEW CONNECTION AT PURBA GOBINDAPUR PH-1 |  |  | BILL/00243/2024-2025 | 102/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 6.06 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | PURBA GOBINDAPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000095/2023-2024 | 217/BD-I | 17/05/2023 | 15/08/2023 | SUPTI ENTERPRISE | 40.92 | 22.25 | 54.36 | 50
5 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PURBA GOBINDAPUR and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW) | Assistant Engineer-I |  | ORD/000058/2025-2026 | 770/BD-I | 22/05/2025 | 06/06/2025 | M/S UNIVERSAL TRADING | 9.01 | 0 | 0 | 0
Total | [13 empty] | 367.69 | 118.64 | 32.27