## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Berhampore | Berhampore Division I | GOBINDAPUR PWSS | SM/16784 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 61/BD-1/14 | 27/04/2023 | 27/04/2023 | Resource Division | 17.81 | 0 | 0 | 0
2 | MURSHIDABAD | Berhampore | Berhampore Division I | GOBINDAPUR PWSS | SM/16784 | New | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | 2096/BD-I/6 | 25/11/2024 | 25/11/2024 | Resource Division | 4.65 | 0 | 0 | 0
3 | MURSHIDABAD | Berhampore | Berhampore Mechanical | GOBINDAPUR PWSS | SM/16784 | New | NEW CONNECTION GOBINDAPUR PH-1 |  |  | BILL/01620/2023-2024 | 459/WBSEDCL-JJM | 18/03/2024 | 18/03/2024 | WBSEDCL | 7.49 | 0 | 0 | 0
4 | MURSHIDABAD | Berhampore | Berhampore Division I | GOBINDAPUR PWSS | SM/16784 | New | GOBINDAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I,Assistant Engineer-II | JE,Junior Engineer | ORD/000045/2023-2024 | 142/BD-I | 15/05/2023 | 27/03/2026 | DEBASISH SARKAR | 73.41 | 10.51 | 14.31 | 30
5 | MURSHIDABAD | Berhampore | Berhampore Division I | GOBINDAPUR PWSS | SM/16784 | New | GOBINDAPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Berhampore Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE,Junior Engineer | ORD/000101/2023-2024 | 219/BD-I | 17/05/2023 | 02/05/2025 | AZAD CONSTRUCTION & CO. | 40.55 | 11.5 | 28.36 | 90
6 | MURSHIDABAD | Berhampore | Berhampore Division I | GOBINDAPUR PWSS | SM/16784 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Gobindrapur" ground water supply scheme in Berhampore Block, under Berhampore Division-I, P.H.E Dte. (Capacity-34 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | Assistant Engineer-II |  | ORD/000036/2024-2025 | 997/BD-I | 20/06/2024 | 20/06/2025 | ACQUA CONSTRUCTION CONSORTIUM | 146.58 | 0 | 0 | 0
7 | MURSHIDABAD | Berhampore | Berhampore Division I | GOBINDAPUR PWSS | SM/16784 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GOBINDAPUR Water Supply Scheme(TW -II) within Berhampore Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer-II | Junior Engineer | ORD/000294/2024-2025 | 100/BD-I | 20/01/2025 | 19/07/2025 | SUJIT KUMAR SAHA | 9.01 | 0 | 0 | 100
Total | [13 empty] | 299.5 | 22.01 | 7.35