## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | MALIPUR PIPED WATER SUPPLY SCHEME. | SM/16785 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 61/BD-1/30 | 27/04/2023 | 27/04/2023 | Resource Division | 18.6 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-II | Berhampore Mechanical | MALIPUR PIPED WATER SUPPLY SCHEME. | SM/16785 | New | NEW CONNECTION MALIPUR PH-1 |  |  | BILL/01490/2023-2024 | 372/WBSEDCL-JJM | 21/02/2024 | 21/02/2024 | WBSEDCL | 5.26 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | MALIPUR PIPED WATER SUPPLY SCHEME. | SM/16785 | New | MALIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000099/2023-2024 | 209/BD-I | 17/05/2023 | 06/05/2025 | PRANAB KUMAR GHOSH | 39.48 | 22.82 | 57.79 | 55
4 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | MALIPUR PIPED WATER SUPPLY SCHEME. | SM/16785 | New | MALIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. . | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000131/2023-2024 | 610/BD-I | 02/08/2023 | 18/01/2026 | ROY CONSTRUCTION (AVIJIT ROY) | 85.64 | 51.33 | 59.94 | 90
5 | MURSHIDABAD | Bhagawangola-II | Central Drilling | MALIPUR PIPED WATER SUPPLY SCHEME. | SM/16785 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.02 | 1.95 | 20
6 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | MALIPUR PIPED WATER SUPPLY SCHEME. | SM/16785 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MALIPUR and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW) | Assistant Engineer-I |  | ORD/000060/2025-2026 | 772/BD-I | 22/05/2025 | 06/06/2025 | M/S GUHA AND ROY ENTERPRISE | 9 | 0 | 0 | 0
Total | [13 empty] | 878.21 | 88.17 | 10.04