## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | KISMATTATLA AND ADJOINING MOUJAS PWSS | SM/16786 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Kismattatla ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000654/2023-2024 | 3688/MEDB | 03/11/2023 | 03/02/2024 | EASTERN INDIA SALES & SERVICE | 20.69 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | KISMATTATLA AND ADJOINING MOUJAS PWSS | SM/16786 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 61/BD-1/24 | 27/04/2023 | 27/04/2023 | Resource Division | 7.05 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-I | Berhampore Mechanical | KISMATTATLA AND ADJOINING MOUJAS PWSS | SM/16786 | New | KISMATTALA PWSS |  |  | BILL/01452/2023-2024 | 345/WBSEDCL-JJM | 15/02/2024 | 15/02/2024 | WBSEDCL | 3.54 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | KISMATTATLA AND ADJOINING MOUJAS PWSS | SM/16786 | New | KISMATTATLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000093/2023-2024 | 215/BD-I | 17/05/2023 | 31/01/2026 | RUDRA NARAYAN GHOSH | 40.74 | 0 | 0 | 25
5 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | KISMATTATLA AND ADJOINING MOUJAS PWSS | SM/16786 | New | KISMATTATLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. [ 2ND Call for WBPHED/EE/BD-I/NIeT-30 of 2022 ¿ 2023 (sl no-02)] | Assistant Engineer-I | Junior Engineer-I | ORD/000125/2023-2024 | 514/BD-I | 25/07/2023 | 09/02/2026 | U TURN CONSTRUCTION | 172.1 | 32.42 | 18.84 | 15
6 | MURSHIDABAD | Bhagawangola-I | Berhampore Division I | KISMATTATLA AND ADJOINING MOUJAS PWSS | SM/16786 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KISMATTATLA and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW). | Assistant Engineer-I |  | ORD/000061/2025-2026 | 773/BD-I | 22/05/2025 | 06/06/2025 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 9.01 | 0 | 0 | 0
Total | [13 empty] | 253.14 | 32.42 | 12.81