## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | GOURIDASPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000084/2023-2024 | 202/BD-I | 17/05/2023 | 22/10/2026 | M/S ROY & BOSE ENTERPRISE | 41.09 | 2.65 | 6.45 | 75
2 | MURSHIDABAD | Lalgola | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | GOURIDASPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000151/2023-2024 | 655/BD-I | 08/08/2023 | 15/08/2026 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 209.18 | 93.25 | 44.58 | 85
3 | MURSHIDABAD | Lalgola | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 61/BD-1/26 | 27/04/2023 | 27/04/2023 | Resource Division | 11.84 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 304/BD-1/9 | 22/02/2024 | 22/02/2024 | Resource Division | 4.82 | 0 | 0 | 0
5 | MURSHIDABAD | Lalgola | Berhampore Mechanical | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Gouridaspur Piped Water Supply Scheme Block Lalgola, District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000567/2024-2025 | 382/MEDB | 12/02/2025 | 01/01/2027 | CHAKRABORTY MINING AND ENGINEERING | 22.73 | 0 | 0 | 5
6 | MURSHIDABAD | Lalgola | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GOURIDASPUR Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer | JE | ORD/000279/2024-2025 | 11/BD-I | 06/01/2025 | 06/04/2025 | HARUN ALL RASHID & BROTHERS | 8.91 | 0 | 0 | 100
7 | MURSHIDABAD | Lalgola | Berhampore Mechanical | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | NEW CONNECTION AT GOURIDASPUR PH-I |  |  | BILL/01460/2024-2025 | 424/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 13.93 | 0 | 0 | 0
Total | [13 empty] | 312.51 | 95.9 | 30.69