## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 61/BD-1/26 | 27/04/2023 | 27/04/2023 | Resource Division | 11.84 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 304/BD-1/9 | 22/02/2024 | 22/02/2024 | Resource Division | 4.82 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | GOURIDASPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000084/2023-2024 | 202/BD-I | 17/05/2023 | 28/01/2026 | M/S ROY & BOSE ENTERPRISE | 41.09 | 0 | 0 | 75
4 | MURSHIDABAD | Lalgola | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | GOURIDASPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000151/2023-2024 | 655/BD-I | 08/08/2023 | 16/02/2026 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 209.18 | 0 | 0 | 85
5 | MURSHIDABAD | Lalgola | Berhampore Mechanical | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Gouridaspur Piped Water Supply Scheme Block Lalgola, District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000567/2024-2025 | 382/MEDB | 12/02/2025 | 12/05/2025 | CHAKRABORTY MINING AND ENGINEERING | 22.73 | 0 | 0 | 0
Total | [13 empty] | 289.67 | 0 | 0