## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | KESABPUR AND ADJOINING MOUJAS PWSS | SM/16788 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 61/BD-1/31 | 27/04/2023 | 27/04/2023 | Resource Division | 15.38 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | KESABPUR AND ADJOINING MOUJAS PWSS | SM/16788 | New | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 304/BD-1/2 | 22/02/2024 | 22/02/2024 | Resource Division | 7.74 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Mechanical | KESABPUR AND ADJOINING MOUJAS PWSS | SM/16788 | New | NEW CONNECTION KESABPUR PH-1 |  |  | BILL/01606/2023-2024 | 425/WBSEDCL-JJM | 12/03/2024 | 12/03/2024 | WBSEDCL | 6.22 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Mechanical | KESABPUR AND ADJOINING MOUJAS PWSS | SM/16788 | New | KESABPUR PH-1 |  |  | BILL/01517/2023-2024 |  | 28/02/2024 | 28/02/2024 | WBSEDCL | 6.22 | 0 | 0 | 0
5 | MURSHIDABAD | Lalgola | Berhampore Division I | KESABPUR AND ADJOINING MOUJAS PWSS | SM/16788 | New | KESABPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000081/2023-2024 | 199/BD-I | 17/05/2023 | 23/12/2025 | AZAD ENTERPRISE | 40.95 | 17.52 | 42.79 | 20
6 | MURSHIDABAD | Lalgola | Berhampore Division I | KESABPUR AND ADJOINING MOUJAS PWSS | SM/16788 | New | KESABPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main , Construction of OHR (Capacity - 200 cum ) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000172/2023-2024 | 664/BD-I | 09/08/2023 | 01/10/2025 | D.N SARKAR AND SONS | 294.7 | 130.11 | 44.15 | 30
7 | MURSHIDABAD | Lalgola | Central Drilling | KESABPUR AND ADJOINING MOUJAS PWSS | SM/16788 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 13.17 | 1.83 | 20
Total | [13 empty] | 1091.45 | 160.8 | 14.73