## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | KALIAGACHI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000082/2023-2024 | 1258/BD-I | 22/12/2023 | 12/09/2025 | SATELLITE CONSTRUCTION | 39.24 | 0 | 0 | 25
2 | MURSHIDABAD | Lalgola | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | KALIAGACHI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000271/2023-2024 | 975/BD-I | 18/10/2023 | 01/04/2025 | PRANAB KUMAR GHOSH | 61.78 | 4.5 | 7.29 | 25
3 | MURSHIDABAD | Lalgola | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 61/BD-1/22 | 27/04/2023 | 27/04/2023 | Resource Division | 13.36 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 304/BD-1/10 | 22/02/2024 | 22/02/2024 | Resource Division | 2.82 | 0 | 0 | 0
5 | MURSHIDABAD | Lalgola | Berhampore Mechanical | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Kaliagachhi Piped Water Supply Scheme Block Lalgola, District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000528/2024-2025 | 314/MEDB | 10/02/2025 | 10/05/2025 | P. K. ENGINEERING | 21.38 | 0 | 0 | 0
6 | MURSHIDABAD | Lalgola | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KALIGACHHI Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer | JE | ORD/000277/2024-2025 | 13/BD-I | 06/01/2025 | 06/04/2025 | HARUN ALL RASHID & BROTHERS | 8.91 | 0 | 0 | 100
7 | MURSHIDABAD | Lalgola | Berhampore Mechanical | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | NEW CONNECTION AT KALIAGACHI PH-I |  |  | BILL/01459/2024-2025 | 423/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 10.43 | 0 | 0 | 0
Total | [13 empty] | 157.92 | 4.5 | 2.85