## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 61/BD-1/22 | 27/04/2023 | 27/04/2023 | Resource Division | 13.36 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 304/BD-1/10 | 22/02/2024 | 22/02/2024 | Resource Division | 2.82 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | KALIAGACHI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000082/2023-2024 | 1258/BD-I | 22/12/2023 | 12/09/2025 | SATELLITE CONSTRUCTION | 39.24 | 0 | 0 | 25
4 | MURSHIDABAD | Lalgola | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | KALIAGACHI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000271/2023-2024 | 975/BD-I | 18/10/2023 | 01/04/2025 | PRANAB KUMAR GHOSH | 61.78 | 0 | 0 | 25
5 | MURSHIDABAD | Lalgola | Berhampore Mechanical | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Kaliagachhi Piped Water Supply Scheme Block Lalgola, District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000528/2024-2025 | 314/MEDB | 10/02/2025 | 10/05/2025 | P. K. ENGINEERING | 21.38 | 0 | 0 | 0
Total | [13 empty] | 138.58 | 0 | 0